## Project Scheduling
i-net Clear Reports
Project Scheduling
This report shows a sample of project scheduling using a gantt chart.
Design
| Task name |  |  |  | Start | End |  |  |  | Days
| Requirements |  |  |  | 2007-02-01 | 2007-02-08
7
| Concept |  |  |  | 2007-02-08 | 2007-02-15
7
| Class design |  |  |  | 2007-02-16 | 2007-02-28
12
| Data structure |  |  |  | 2007-03-01 | 2007-03-12
11
| GUI design |  |  |  | 2007-03-13 | 2007-03-17
4
| Final check |  |  |  | 2007-03-18 | 2007-03-20
2
Statistic
Tasks sorted by their effort
[7 empty] | Duration of current phase: |  | 43
Programming
| Task name |  |  |  | Start | End |  |  |  | Days
| Coding Feature |  |  |  | 2007-03-21 | 2007-04-10
20
| Coding DB |  |  |  | 2007-04-11 | 2007-04-24
13
| Coding GUI |  |  |  | 2007-04-25 | 2007-05-12
17
| Unit Tests |  |  |  | 2007-05-13 | 2007-05-17
4
Statistic
Tasks sorted by their effort
[7 empty] | Duration of current phase: |  | 54
Test
| Task name |  |  |  | Start | End |  |  |  | Days
| Build Test Plans |  |  |  | 2007-05-18 | 2007-05-22
4
| Review |  |  |  | 2007-05-23 | 2007-05-25
2
| Execute Tests |  |  |  | 2007-05-26 | 2007-05-27
1
| Fixing Defects |  |  |  | 2007-05-28 | 2007-06-09
12
| Regress Test |  |  |  | 2007-06-10 | 2007-06-12
2
| Deliver Beta Build |  |  |  | 2007-06-13 | 2007-06-15
2
Statistic
Tasks sorted by their effort
[7 empty] | Duration of current phase: |  | 23
|  |  | © Copyright 1996 - 2025, i-net software GmbH; All rights Reserved. |  |  |  |  | Page 1 of 1